## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Team | Week 1 – Day 2 | Noise and special characters present in raw dataset | Sprint 1 |  | Standards | Applied text cleaning and regex preprocessing | Week 1 – Day 3 | Closed | Resolved during preprocessing
2 | Team | Week 1 – Day 4 | Tokenization inconsistency for long emails | Sprint 1 |  | Logical | Improved tokenization logic | Week 1 – Day 5 | Closed | Stable token output achieved
3 | Team | Week 2 – Day 3 | Class imbalance in urgency labels | Sprint 1 |  | Logical | Used evaluation metrics like F1-score and recall | Week 2 – Day 4 | Closed | Handled via evaluation strategy
4 | Team | Week 3 – Day 3 | Logistic Regression underperforming on minority class | Sprint 2 |  | Logical | Introduced SVM for better classification | Week 3 – Day 4 | Closed | Improved performance
5 | Team | Week 4 – Day 1 | SVM training time slightly high | Sprint 2 |  | Maintainability | Tuned hyperparameters | Week 4 – Day 2 | Closed | Performance optimized
6 | Team | Week 5 – Day 2 | LSTM model training taking high computation time | Sprint 3 |  | Maintainability | Reduced epochs and batch size | Week 5 – Day 3 | Closed | Training stabilized
7 | Team | Week 6 – Day 1 | DistilBERT input formatting issue | Sprint 3 |  | Logical | Fixed tokenizer and input pipeline | Week 6 – Day 2 | Closed | Model working correctly
8 | Team | Week 6 – Day 2 | Difficulty comparing outputs of multiple models | Sprint 3 |  | Maintainability | Standardized evaluation metrics | Week 6 – Day 3 | Closed | Comparison simplified
9 | Team | Week 6 – Day 3 | Rule-based and ML outputs mismatch | Sprint 3 |  | Logical | Developed hybrid logic for consistency | Week 6 – Day 4 | Closed | Outputs aligned
10 | Team | Week 7 – Day 2 | Visualization requirements unclear initially | Sprint 4 |  | User Interface | Defined key metrics for dashboard | Week 7 – Day 3 | Closed | Requirements finalized
11 | Team | Week 8 – Day 1 | API integration issues during deployment | Sprint 5 |  | Logical | Debugged API and model connection | Week 8 – Day 2 | Closed | Integration successful
12 | Team | Week 8 – Day 3 | Minor inconsistencies in final output format | Sprint 5 |  | Standards | Standardized response format | Week 8 – Day 4 | Closed | Final system stable

## Sheet2
Logical
User Interface
Maintainability
Standards
Others